## Project Backlog
ID | Theme | Title | As a/an | I want to… | so that… | Confirmations | Notes | Priority | Status /name/blank /done/accepted | Time Estimate | Actual Time
6 | Site security | Librarian log in | librarian | log in to the system | I can access features only available to librarians | Login Success: User is logged in and redirect to librarian home page. - "Remember me" checked - User automatically logs in next time. - "Remember me" not checked - Forced log in next time. Login Failure: Display message - User name not found: Create an account - Password incorrect: Recover password Logout Success: User is redirected to unauthenticated users home page. |  | 1 |  | 8
10 | Materials | Add Materials | librarian | add new material to the materials catalog | I can make newly purchased material available to our patrons and the public | Librarian cannot submit form until all required fields are complete. Required fields are denoted with an *. If a required field is missing on submission, a message is displayed. Photo must be .jpg format. Photo must be renamed to the material's ISBN number. If no photo is available, the system must indicate this. User must be redirected after item is added to the database. | Must also be able to upload a photo of the material and have it automatically renamed to the ISBN# of the material. | 2 |  | 12
10 | Materials | Delete Materials | librarian | delete old material from the materials catalog | material we have removed from the shelves and no longer have in our collection is removed from the catalog |  |  | 2 |  | 4
10 | Materials | Update Materials | librarian | update existing information in the materials catalog | I can correct errors and change material information as necessary |  |  | 2 |  | 4
11 | Patron | Add Patron | librarian | add a new patron to the system | they can check out library materials |  |  | 4 |  | 12
11 | Patron | Delete Patrons | librarian | delete a patron record from the system | when patrons move away or stop using the library they are not unnecessarily left in the system |  |  | 4 |  | 4
11 | Patron | Update Patrons | librarian | update existing patron records in the system | I can change their address, phone number, and email as needed |  |  | 4 |  | 4
8 | Check In/Out | Material Check-out | librarian | check library materials out to patrons | the library has a record of who has borrowed material from the library |  |  | 5 |  | 12
9 | Check In/Out | Material Check-in | librarian | check in library material that has been returned by a patron | the materail is available for another patron to borrow |  |  | 6 |  | 12
12 | Search | Librarian materials search | librarian | search the materials catalog | I can locate items on the shelves |  |  | 7 |  | 12
13 | Search | Librarian patron search | librarian | search patron records | I can locate account details of a specific patron |  |  | 8 |  | 12
27 | Check In/Out | Manual overdue report | librarian | manually run an overdue report | I can locate overdue materials and see the details of the patron that has them checked out |  |  | 9 |  | 12
15 | Search | Public material search | public user | search the materials catalog | I can determine if the library has the material I am looking for and if it it available or checked out |  |  | 10 |  | 4
17 | Mobile | Mobile device contact | public user | access the library's web site on a mobile device | I can check library hours and call or email the library |  | When the user touches the phone number, it should open the phone application and fill in the number on the phone so all they have to do is click "dial". When the user touches the email address, it should open the email application and fill in the to: and subject: so all they need to do is type the message and click "send". | 11 |  | 8
17 | Mobile | Mobile device search | public user | search the library's materials catalog on a mobile device | I can determine if the library has the material I am looking for and if it it available or checked out |  |  | 12 |  | 4
18 | Site security | Patron log in | patron | log in to the system | I can access my account details |  |  | 14 |  | 2
22 | Search | Patron material search | patron | search the materials catalog | I can determine if the library has the material I am looking for and if it it available or checked out |  |  | 15 |  | 2
| Non-functional | Site design |  | Masterpages, external CSS, sitemap control, menu control | [5 empty] | 4
Non-functional
Non-functional
Optional
Optional
| Derived from: | http://www.mountaingoatsoftware.com/blog/a-sample-format-for-a-spreadsheet-based-product-backlog | [6 empty] | Person-hours of work: | 132 | 0
[9 empty] | Assuming 70% velocity, the hours it will take to actually complete the work: | 188.5714
[8 empty] | Hours of work (including 70% velocity) that can be completed by a 4 person team in 1 iteration working 2 hour days: | 112
[8 empty] | Hours of work (including 70% velocity) that can be completed by a 3 person team in 1 iteration working 2 hour days: | 84

## User Stories
ID | Title | As a/an | I want to… | so that… | Priority | Time Estimate
6 | Librarian log in | librarian | log in to the system | I can access features only available to librarians | 1 | 8
10 | Add Materials | librarian | add new material to the materials catalog | I can make newly purchased material available to our patrons and the public | 2 | 12
10 | Delete Materials | librarian | delete old material from the materials catalog | material we have removed from the shelves and no longer have in our collection is removed from the catalog | 2 | 4
10 | Update Materials | librarian | update existing information in the materials catalog | I can correct errors and change material information as necessary | 2 | 4
11 | Add Patron | librarian | add a new patron to the system | they can check out library materials | 4 | 12
11 | Delete Patrons | librarian | delete a patron record from the system | when patrons move away or stop using the library they are not unnecessarily left in the system | 4 | 4
11 | Update Patrons | librarian | update existing patron records in the system | I can change their address, phone number, and email as needed | 4 | 4
8 | Material Check-out | librarian | check library materials out to patrons | the library has a record of who has borrowed material from the library | 5 | 12
9 | Material Check-in | librarian | check in library material that has been returned by a patron | the materail is available for another patron to borrow | 6 | 12
12 | Librarian Materials Search | librarian | search the materials catalog | I can locate items on the shelves | 7 | 12
13 | Librarian Patron Search | librarian | search patron records | I can locate account details of a specific patron | 8 | 12
27 | Manual Overdue Report | librarian | manually run an overdue report | I can locate overdue materials and see the details of the patron that has them checked out | 9 | 12
15 | Public search | public user | search the materials catalog | I can determine if the library has the material I am looking for and if it it available or checked out | 10 | 4
17 | Mobile device contact | public user | access the library's web site on a mobile device | I can check library hours and call or email the library | 11 | 8
17 | Mobile device search | public user | search the library's materials catalog on a mobile device | I can determine if the library has the material I am looking for and if it it available or checked out | 12 | 4
18 | Patron log in | patron | log in to the system | I can access my account details | 14 | 2
22 | Patron search | patron | search the materials catalog | I can determine if the library has the material I am looking for and if it it available or checked out | 15 | 2
19 | Patron account view | patron | view my account details | to see what items I currently have checked out and what address, phone, and email address are on file | 16 | 4
[5 empty] | Person-hours of work: | 132
[5 empty] | Assuming 70% velocity, the hours it will take to actually complete the work: | 188.5714
|  |  |  | Hours of work (including 70% velocity) that can be completed by a 4 person team in 1 iteration working 8 hour days: | 448
|  |  |  | Hours of work (including 70% velocity) that can be completed by a 3 person team in 1 iteration working 8 hour days: | 336

## Burndown Chart
Date | Estimated Time | Actual Time
1 | 188.6 | 129
5 | 161.6572 | 126
10 | 134.7144 | 106
15 | 107.7716 | 89
20 | 80.8288 | 77
25 | 53.886 | 61
30 | 26.9432 | 45
35 | 0 | 0
Chris | Hours | Activity
2013-04-03 | 3 | Database development
2013-04-11 | 1 | database development
| 3 | set up login for librarians and patrons
| 6 | add patrons
| 1 | view all patrons
2013-04-13 | 1 | Ajax validation for new patron
2013-04-15 | 5 | Edit and Delete patrons
2012-04-16 | 1 | Password recovery and patron details edits
2013-04-19 | 1 | Edits to checkin/checkout
2013-04-22 | 2 | Worked on add materials/image upload
| 1 | Cleaned up drive
2013-04-23 | 2 | Finished uploading images
| 1 | Images working server wide
| 1 | Fixed user details and delete patrons
2013-04-28 | 1 | Worked on patron details
2013-04-29 | 3 | Overdue report, developers choice
| 1 | Checkout fix
2013-04-30 | 1 | Second Developers Choice
| 1 | Security validation
2013-05-03 | 2 | Mobile Website
2013-05-04 | 2 | Validations added
| 1 | ERD
2013-05-05 | 3 | Bug Fixes
2013-05-06 | 3 | Minor edits
Megan
2013-04-10 | 2 | Draft of wireframe and screen sketches
| 4 | Patron librarian search
2013-04-17 | 1 | Patron search update,
| 2 | header &menu updates
2013-04-18 | 1 | Date added to master
| 1 | Patrons/Materials view all edits
| 1 | Master page edits
2013-04-19 | 5 | Check in/checkout
2013-04-22 | 1 | Added map with link
| 1 | Images to details view
2013-04-23 | 3 | Details view for patrons and users
2013-04-29 | 1 | Edit add patrons
2013-04-30 | 1 | Cursor focus
| 2 | Added titles to pages and fixed material details
2013-05-03 | 2 | Editing documentation
2013-05-04 | 10 | CSS
2013-05-05 | 3 | Centering, titles and edit screen sketches
2013-05-06 | 3 | Minor Edits
Connie
2013-04-10 | 3 | Activity and sequence diagrams
2013-04-16 | 1 | Edited activity and sequence diagrams
| 6 | Add Materials
2013-04-25 | 4 | Test Plan
2013-04-30 | 1 | Added TR references
| 2 | Delete Materials
| 2 | Update Materials
2013-05-06 | 2 | Class Diagram
| 4 | Testing

## Backlog
Theme | Details | Completed Y/N/IP | Person who did this | Priority | Time Estimate | Actual Time
Scheduling
| Develop and regularly update spreadsheet | Y | Chris / Megan | 1 | 2 | 3
| Develop and regularly update burndown chart | Y | Connie | 2 | 1
| Explanation of how this worked | N
Database Component
| Develop a database diagram | Y | Chris | 5 | 2 | 1
| Develop the complete database for iteration 1 | Y | Chris | 5 | 12 | 4
| Database should be populated with sample patron and materials | Y | Connie | 5 | 4 | 4
Use case diagram
| Develop use case diagram for iteration 1 | Y | Megan | 5 | 2 | 2
Use case, activity, sequence for 8/9
| Develop activity diagram | Y | Connie/Megan | 5 | 2 | 2
| Develop sequence diagram | Y | Connie | 5 | 2 | 2
| Develop use case documents | Y | Connie | 5 | 4 | 1
Test Plan for 8/9
| Complete all confirmations on Project Backlog | Y | Megan | 5 | 2 | 4
| Create a test plan including all required steps and possible outcomes | Y | Connie | 5 | 4 | 4
Class Diagram
| Develop a class diagram | Y | Connie | 5 | 2 | 2
Github
| Everyone should push commits on github | Y | All | 1 | N/A | N/A
Asp pages for
| Wireframe diagram | Y | Megan | 1 | 1 | 1
| Sitemap diagram | Y | Megan | 5 | 2 | 1
| Screen sketches | Y | Megan | 5 | 2 | 3
Security
| Librarians can login so they can access features only available to librarians | Y | Chris | 1 | 8 | 3
| Patrons can login so they can view account details | Y | Chris | 12 | 2 | 3
Materials
| Librarians can add materials | Y | Connie | 2 | 12 | 8
| Librarians can delete materials | Y | Connie | 2 | 4 | 2
| Librarians can update materials | Y | Connie | 2 | 4 | 2
Patron
| Librarians can add patrons | Y | Chris | 4 | 12 | 4
| Librarians can delete patrons | Y | Chris | 4 | 4 | 1
| Librarians can update patrons | Y | Chris | 4 | 4 | 1
Check In/Checkout
| Librarians can check out materials to patrons | Y | Megan | 5 | 12 | 3
| Librarians can check in materials patrons have rented | Y | Megan | 6 | 12 | 2
| Librarians can manually create an overdue report | Y | Chris | 9 | 12 | 2
Search
| Patrons can search materials in the catalog | Y | Megan | 15 | 2 | 1
| Public Users can search materials in the catalog | Y | Megan | 10 | 4 | 1
| Librarians can search materials in the catalog | Y | Megan | 7 | 12 | 2
| Librarians can search patron records | Y | Megan | 8 | 12 | 1
Mobile
| Public can contact library by phone call or email from mobile device | Y | Chris | 11 | 8 | 1
| Public can search library catalog by mobile device | Y | Chris | 12 | 4 | 1
Developer's Choice
| Verify material ID exists in system | Y | Chris | 17 | 4 | 1
| Verify patron ID exists in system | Y | Chris | 17 | 4 | 1
Non-functional
| Masterpages | Y | Chris | 16 | 1 | 1
| External CSS | Y | Megan | 16 | 1 | 10
| Menu Control | Y | Megan | 16 | 1 | 1
| Sitemap Control | Y | Chris | 16 | 1 | 1
| Extra Testing | Y | Connie | 16 | 2 | 3